## Burndown
DiLab Foresight Framework — Sprint 5 (Final Polish)
Burndown · Story Points · 22 Jun 2026 – 06 Jul 2026
Committed: 55 SP ¦ Done by 28 Jun: 21 SP ¦ Remaining: 34 SP
Date | Day | Ideal (Guideline) | Remaining
22 Jun | Mon | 55 | 55
23 Jun | Tue | 51.1 | 53
24 Jun | Wed | 47.1 | 49
25 Jun | Thu | 43.2 | 45
26 Jun | Fri | 39.3 | 42
27 Jun | Sat | 35.4 | 38
28 Jun | Sun | 31.4 | 34
29 Jun | Mon | 27.5 | 29
30 Jun | Tue | 23.6 | 24
01 Jul | Wed | 19.6 | 19
02 Jul | Thu | 15.7 | 14
03 Jul | Fri | 11.8 | 10
04 Jul | Sat | 7.9 | 7
05 Jul | Sun | 3.9 | 4
06 Jul | Mon | 0 | 0
Note: trend until 28 Jun = actual · afterwards = planned completion (S8–S12).

## Sprint Backlog
Sprint 5 – Sprint Backlog
Key | Story | SP | Assignee | Status
DFF-11 | S1 · Make pipeline domain-agnostic | 8 | Paul | Done
DFF-12 | S2 · Fix positivity bias (split-scoring) | 8 | Christian | Done
DFF-13 | S3 · Null-model significance test | 5 | Aditya | Done
DFF-17 | S7 · Connect R&S local inference endpoints | 3 | Paul | To Do
DFF-18 | S8 · ML technology-driver extraction | 8 | Aditya | In Progress
DFF-19 | S9 · Polish UI | 5 | Adam | In Progress
DFF-20 | S10 · LLM-as-a-Judge evaluation layer | 8 | Lovepreet | In Progress
DFF-21 | S11 · Domain-agnostic on agriculture corpus | 5 | Christian | In Progress
DFF-22 | S12 · Refine contrastive CCA | 5 | Paul | In Progress
| Committed | 55
| Done (28 Jun) | 21